## Sheet1
Sprint 4 Plan | Time Est. | https://piazza.com/class_profile/get_resource/ktxz1nfkf8b5ai/kudlrkyx9aj6r7
As a user, I want to be able to know if the player I am searching is available in the selected region or not | Total: 4 | Heading |  | Goal
Set up the search not found page. | 4 | Document Name | Sprint 4 Plan | To wrap up the application and be able to provide an appropriate demo
|  | Product Name | Game Performance Tracker
As a user, I want to have a good visual and functional experience using the Web application | Total: 8 | Team Name | Leaguer Devers
Adjust the Match history page UI for the better look. | 2 | Completion Date | 2021-11-30
Adjust the Leaderboard page UI for the better look. | 2 | Revision No. | 0
Adjust the landing page UI for the better look | 2 | Revision Date | 2021-11-18
Adjust the overview page UI for the better look | 2 | Team Roles |  | Initial Task Assignment
|  | Eric | Scrum Master | Eric | Work on the footer and Navbar, write up documentation, finish unit testing for search bar
As a product Owner, I want to see a functional demo that is presentable and well tested | Total: 8 | Hao | Member | Hao | Improve and implement the desgins for several pages
Make Footer fully functional | 2 | Jack | Member | Jack | Improve and implement the desgins for several pages
Make Navbar fully functional | 2 | Mason | Member | Mason | work on the 404 not found page
Complete system testing | 2 | Sunny | Product Owner | Sunny | finish unit testing for leaderboard, establish endpoint, implement transition animations
Complete Unit testing | 2 |  |  | Scrum Times
Tuesday, 7PM
As a product owner, I want to have a general documentation of the application so that it can be maintainable | Total: 2 |  |  | Thursday, 4:30PM
Complete code documentation | 2 |  |  | Sunday, 3PM