## Sheet1
Sprint 3 Plan | Time Est. | https://piazza.com/class_profile/get_resource/ktxz1nfkf8b5ai/kudlrkyx9aj6r7
As a player, I want to see my match history so that I can know how I perfrom recently. | Total: 12 | Heading |  | Goal
Match history page UI implementation | 5 | Document Name | Sprint 3 Plan | To implement most part of the figma design with some kind of data
Match history backend endpoint setup | 2 | Product Name | Game Performance Tracker
Match data computation | 5 | Team Name | Leaguer Devers
|  | Completion Date | 2021-11-16
As a player, I would like to be able to see a leaderboard of current top ranked player. | Total: 8 | Revision No. | 0
Leaderboard page UI implementation | 5 | Revision Date | 2021-11-02
Leaderboard backend endpoint setup | 3 | Team Roles |  | Initial Task Assignment
|  | Eric | Member | Eric | Leaderboard backend endpoint setup
As a player, I want to have a good looking Landing page so that I can get comfortable first impression. | Total: 5 | Hao | Scrum Master | Hao | Match history page UI implementation
Landing page design | 2 | Jack | Member | Jack | Landing page design
Landing page UI implementation | 3 | Mason | Member | Mason | Match history backend endpoint setup
|  | Sunny | Product Owner | Sunny | Create Unit test before or after finishing a feature/function
As a Player, I want an application that is tested in every aspect so that I don't have to worry about it crashing. | Total: 5 |  |  | Scrum Times
Create Unit test before or after finishing a feature/function | 5 |  |  | Tuesday, 7PM
Thursday, 430PM
Sunday 3PM
Initial Scrum Board
NULL